## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | DevHub – A Next-Generation Learning Platform
| Project Manager: | Fatima Shahid
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five day sprint.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent daily on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Day | This is the number of hours spent on a given task for the day.
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Effort (Hours) | 20 | 17 | 11 | 5 | 2 | 0
Ideal Effort (Hours) | 20 | 16 | 12 | 8 | 4 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Quiz/Challenge System | 6 | 2 | 2 | 2 | 0 | 0 | 6
Dynamic Quiz UI | 5 | 0 | 1 | 2 | 1 | 1 | 5
User Progress Dashboard | 4 | 1 | 1 | 1 | 1 | 0 | 4
Interactive Exercises | 5 | 0 | 2 | 1 | 1 | 1 | 5