## Sheet1
DevHub – Meeting Minutes Summary (Sprint 1 to 6)
Sprint | Date | Time | Duration | Meeting Type | Attendees | Agenda / Discussion Points | Decisions / Outcomes
1 | 2025-02-26 | 03:00 PM – 03:30 PM | 30 mins | Mid-Sprint Sync | Fatima, Rushba, Saad | GitHub branching issues, schema adjustments | Branching rules enforced, schema finalized
2 | 2025-03-04 | 03:15 PM – 03:45 PM | 30 mins | Mid-Sprint Sync | Full Team | UI inconsistencies, SEO confusion | Used templates, SEO responsibilities reassigned
3 | 2025-03-12 | 04:00 PM – 04:30 PM | 30 mins | Mid-Sprint Sync | Full Team | Backend CRUD, API connection, MongoDB issues | Prioritized integration, deferred docs to Sprint 4
4 | 2025-03-28 | 03:00 PM – 03:30 PM | 30 mins | Mid-Sprint Sync | Full Team | Ratings spam, email testing, API limits | Added spam control, tested emails, limited APIs
5 | 2025-04-04 | 03:30 PM – 04:00 PM | 30 mins | Mid-Sprint Sync | Full Team | Quiz logic issues, dashboard state sync | Refactored quiz schema, used hooks for sync
6 | 2025-04-10 | 04:00 PM – 04:30 PM | 30 mins | Mid-Sprint Sync | Full Team | Heatmap tool setup, accessibility retesting | Mobile tested, Hotjar refined, WCAG checklist updated