## Sheet1
DevHub – Meeting Minutes Summary (Sprint 1 to 6)
Sprint | Meeting Type | Date | Time | Duration | Attendees | Agenda / Discussion Points | Decisions / Outcomes
1 | Sprint Planning | Wed, Mar 5, 2025 | 04:00 PM – 04:45 PM | 45 mins | Fatima, Rushba, Saad | GitHub setup, schema delays, branching confusion | Branching policy set, schema finalized
2 | Sprint Planning | Wed, Mar 12, 2025 | 03:30 PM – 04:15 PM | 45 mins | Fatima, Rushba, Saad | UI planning, SEO basics, Figma templates usage | Tasks divided, SEO learning assigned
3 | Mid-Sprint Sync | Wed, Mar 19, 2025 | 04:00 PM – 04:30 PM | 30 mins | Full Team | Backend CRUD status, integration, MongoDB design | Prioritized frontend/backend sync, deferred docs
4 | Mid-Sprint Sync | Wed, Mar 26, 2025 | 03:00 PM – 03:30 PM | 30 mins | Full Team | Rating system, email reliability, social API limits | Added spam control, email testing, limited APIs
5 | Sprint Planning | Wed, Apr 2, 2025 | 04:15 PM – 05:00 PM | 45 mins | Full Team | Plan for quizzes, progress dashboard, interactive snippets | Assigned features module-wise, used schema templates
6 | Sprint Review Prep | Wed, Apr 9, 2025 | 05:00 PM – 05:30 PM | 30 mins | Full Team | Analytics integration, accessibility rechecks, performance fix | Confirmed tracking setup, screenshots finalized